## Sheet1
Sprint | Week | Task | Assigned To | Start | End Date | Duration
Sprint 1 | 1 | Research Tech Stack | Mohamed Afnan | 2026-01-27 | 2026-01-31 | 4
|  | Sprint Planning, Job allocation, Requirement gathering | Saad Wajid | 2026-01-29 | 2026-02-02 | 4
|  | Design wireframes (login UI) | Christos Kladeftiras | 2026-01-29 | 2026-02-01 | 3
|  | Finalize requirements, define Product Backlog | Bader Aljedyani | 2026-01-28 | 2026-01-30 | 2
| 2 | Create User Stories | Christos Kladeftiras | 2026-02-04 | 2026-02-07 | 3
|  | Generate Sprint Backlog | Bader Aljedyani | 2026-02-03 | 2026-02-05 | 2
|  | Architect UML & DFD diagrams | Mohamed Afnan | 2026-02-03 | 2026-02-08 | 5
|  | Update Product Backlog | Saad Wajid | 2026-02-03 | 2026-02-05 | 2
| 3 | Flask app setup, database initialisation | Bader Aljedyani | 2026-02-11 | 2026-02-15 | 4
|  | Conduct scrum meetings, create Logbook | Christos Kladeftiras | 2026-02-10 | 2026-02-13 | 3
|  | Create templates for landing, home, login/registration pages | Saad Wajid | 2026-02-11 | 2026-02-15 | 4
|  | Refine product backlog, created requirements file | Mohamed Afnan | 2026-02-10 | 2026-02-13 | 3
|  | Routes setup - home, landing, login & register pages | Spandana | 2026-02-13 | 2026-02-16 | 3
| 4 | Operational user authentication logic | Saad Wajid | 2026-02-19 | 2026-02-23 | 4
|  | Start Project Cost Estimation metrics calculation | Mohamed Afnan | 2026-02-17 | 2026-02-21 | 4
|  | Create landing page | Bader Aljedyani | 2026-02-19 | 2026-02-23 | 4
|  | Validate system requirements & revise product backlog | Spandana | 2026-02-17 | 2026-02-20 | 3
|  | Design UI - login/register pages | Christos Kladeftiras | 2026-02-21 | 2026-02-23 | 2
Review Week |  | Sprint Review | All | 2026-02-24 | 2026-03-02 | 6
Sprint 2 | 5 | Refactor user auth - OTP verification | Mohamed Afnan | 2026-03-05 | 2026-03-07 | 2
|  | Create Sprint backlog for sprint 2 | Spandana | 2026-03-04 | 2026-03-07 | 3
|  | Setup auth system and styled templates. | Christos Kladeftiras | 2026-03-05 | 2026-03-06 | 1
|  | Create Product Backlog 2 | Bader Aljedyani | 2026-03-04 | 2026-03-06 | 2
|  | Implement organisation login & forgot-password function | Saad Wajid | 2026-03-05 | 2026-03-08 | 3
| 6 | Create Educational Games | Christos Kladeftiras | 2026-03-10 | 2026-03-15 | 5
|  | Create Gantt Chart | Bader Aljedyani | 2026-03-12 | 2026-03-15 | 3
|  | Create Animal templates for School Library | Spandana | 2026-03-12 | 2026-03-14 | 2
|  | Update Product Backlog | Saad Wajid | 2026-03-10 | 2026-03-12 | 2
|  | Implement chat feature & design REST APIs. | Mohamed Afnan | 2026-03-10 | 2026-03-15 | 5
| 7 | Create all Flask Forms and DB models | Spandana | 2026-03-18 | 2026-03-22 | 4
|  | Risk Assessment Matrix | Saad Wajid | 2026-03-19 | 2026-03-21 | 2
|  | Improv chat UI & usablity | Mohamed Afnan | 2026-03-18 | 2026-03-21 | 3
|  | Start Final Project Report | Christos Kladeftiras | 2026-03-17 | 2026-03-23 | 6
|  | Create Personal Profile, Public Library & Compilation Page | Bader Aljedyani | 2026-03-18 | 2026-03-22 | 4
| 8 | Route setup - Schools/Communities, Feature Popularity measure | Bader Aljedyani | 2026-03-25 | 2026-03-28 | 3
|  | Update Project Cost Metrics + Final sprint review + project wrap-up | Mohamed Afnan | 2026-03-25 | 2026-03-30 | 5
|  | Render Common Room, Assignments/Workshops section | Saad Wajid | 2026-03-25 | 2026-03-29 | 4
|  | Finalise Gantt Chart | Spandana | 2026-03-25 | 2026-03-30 | 5
|  | Implement the backend logic - School Library, Common Room | Christos Kladeftiras | 2026-03-25 | 2026-03-29 | 4