## Sprint 1
Sprint 1 Backlog
No. | Goal | Function | Item No. | Urgency | Jobs | Resource | Duration (Weeks)
1 | Complete Landing Page | Sales | 1 | Must | Design Landing Page | Bader Saad | 2
2 | Complete Login Page | User Authentication | 37 | Must | Design Login Page Create Login Backend Connect to Database | Christos | 1
3 | Complete Register Page | User Authentication | 41 | Must | Design Register Page Create Register Backend Connect to Database | Christos Saad | 1
4 | Initialise Database | Data Storage & Backend Setup | 41 | Must | Create .db file Initialise Tables and SQL schema | Bader | 1
5 | Initialise Requirements | Program Functionality | 41 | Must | Create requirements.txt file Identify project dependencies Add dependencies and versions to requirements.txt file | Afnan | 1

## Sprint 2
Sprint 2 Backlog
No. | Goal | Function | Item No. | Urgency | Jobs | Resource | Duration (Weeks)
1 | Complete Landing Page | Sales | 1 | Must | Design Landing Page | Bader Saad | 2
2 | Complete Login Page | User Authentication | 37 | Must | Design Login Page Create Login Backend Connect to Database | Christos | 1
3 | Complete Register Page | User Authentication | 41 | Must | Design Register Page Create Register Backend Connect to Database | Christos Saad | 1
4 | Make OTP System | User Authentication and Email Verification | 37 | Must | Design OTP Page Add Email functionality and OTP entering area Create backend for user verification | Afnan | 1
5 | Change Password Functionality | Account Recovery | 37 | Must | Design Change password page Ability to send email to users with change password details Create backend for updating password | Afnan | 1
6 | Organisation Login | User Authentication | 16 | Must | Allow Organisations to generate unique access codes Allow users to register with organisation using access codes Design OTP page | Afnan | 1
7 | Initialise Requirements | Program Functionality | 41 | Must | Create requirements.txt file Identify project dependencies Add dependencies and versions to requirements.txt file | Afnan | 1
8 | Initialise Database | Data Storage & Backend Setup | 41 | Must | Create .db file Initialise Tables and SQL schema | Bader | 1
9 | Complete Home Page | Website Navigation | 31 | Must | Design Home Page Implement Routes to other pages | Saad | 1
10 | Complete Chat System | Communication and Collaboration | 5 | Must | Create function to get allowed users to talk to Integrate web sockets to enable real time chat updates Create search user option to search for a specific user to chat to | Afnan | 2
11 | Complete Common Room | Communication and Collaboration | 8 | Could | Create display for common room messages and replies Create ability to create common room messages and reply to them | Saad Spandana | 1
12 | Materials Page | Education and Learning | 1 | Must | Create ability for teachers to create educational materials Allow students to view education materials | Saad Spandana | 1
13 | Create Workshops | Practical Work | 2 | Must | Create option for teachers to create a workshop activity Create ability for students to submit their work for the workshop | Saad Spandana | 1
14 | Complete Assignments Page | Education and Examining Progress | 1 | Must | Create option for teacher to create assignments Create option to let students submit assignments Allow teachers to grade assignments and provide feedback Allow students to respond to feedback | Saad Spandana | 1
15 | Add games | Recreation | 32 | Must | Create wordle game Create riddler game Link them using a games page | Christos | 2
16 | Profile Page | Personalisation and Customisability | 4 | Must | Create profile card displaying profile details Create change avatar section Enable customisability through profile themes | Saad | 1
17 | Organisation Page | Organisation View and Access | 21 | Must | Create display for organisation details Show a list of links to go to library, chat etc Create a list of courses provided | Saad | 1
18 | Organisation Library | Explore Contributions | 20 | Must | Create a list of contributions of the organisation Dont show students' names Allow organisation members to add more contributions | Saad | 1
19 | Organisation Admin Tools | Organisation Management and Control | 18 | Must | Create option for organisation admins to add users Give admins ability to issue unique access codes | Christos | 1
20 | Course Page | Course View and Access | 3 | Must | Display course details Create buton navigation links to each related page | Saad Spandana | 1
21 | Public Library | Explore Contributions | 33 | Must | Create a list of all contributions Create a moderation system to ensure contributions aren't inappropriate Don't show names on students' contributions to maintain privacy Allow registered members to add contributions | Bader | 1
22 | Schools Page | Explore Schools and Contributions | 33 | Must | Design Schools Page Create the list of schools | Bader | 1
23 | Communities Page | Explore Schools and Contributions | 33 | Must | Design Communities Page Create the list of communities | Bader | 1
24 | Programs Page | View Programs and Sightings | 33 | Must | Create a list of all animal programs containing information about each animal Create a upload sightings option to allow users to upload sightings of certain animals | Bader Spandana | 2
25 | System Admin Tools | System Administration and Moderation | 36 | Must | Create option to create new organisation Create moderation area to allow system admin to moderate contributions | Christos | 1
26 | Manager Tools | Business Strategy | 25 | Could | Create feature popularity display Create subscription data feature | Christos | 1